AgroHouse Foundation™  AGHF Inc. d/b/a AgroHouse Foundation

Event Operations Checklist (Template)

[EVENT NAME] — [EVENT DATE]

# 90 Days Before Event

☐  Confirm event date, venue, and permits (Vendors)

☐  Finalize Sponsorship Strategy and sponsorship tiers (Sponsors)

☐  Open vendor and sponsor applications (Vendors / Sponsors)

☐  Recruit Fundraiser Committee members; distribute Committee Member Agreements (Volunteers)

☐  Draft Vendor and Sponsor Information Packets (Marketing)

☐  Confirm Donation Acceptance Policy and Cash Handling Policy are Board-adopted (Cash Handling / Documentation)

☐  Identify insurance needs for the event and confirm event coverage with AGHF Inc.'s insurer (Safety)

# 60 Days Before Event

☐  Follow up on vendor and sponsor applications; begin confirming bookings (Vendors / Sponsors)

☐  Launch event marketing and social media announcements (Marketing)

☐  Begin recruiting volunteers; open Volunteer Registration Forms (Volunteers)

☐  Confirm any special contests or activities (e.g., pie contest, cook-off) rules, categories, and judging plan, if applicable (Vendors)

☐  Request in-kind donations for bake sale, contests, and event supplies, as applicable (Donations)

☐  Confirm site layout, electrical needs, and vendor booth map (Vendors)

# 30 Days Before Event

☐  Close or set a deadline for vendor and sponsor applications (Vendors / Sponsors)

☐  Confirm all sponsor logo files and recognition materials received (Sponsors / Marketing)

☐  Assign volunteer roles and shifts based on registration forms (Volunteers)

☐  Confirm cash boxes, starting funds, and cash handling assignments (Cash Handling)

☐  Order or confirm signage, tables, tents, and event day supplies (Vendors)

☐  Distribute Vendor and Volunteer Liability Waivers / Hold Harmless Agreements for signature (Documentation / Safety)

# 14 Days Before Event

☐  Send final event details and setup times to all vendors (Vendors)

☐  Send final shift confirmations to all volunteers (Volunteers)

☐  Confirm all in-kind and food-donation logistics (Donations)

☐  Finalize event day schedule and share with committee (Documentation)

☐  Confirm safety/emergency plan, first aid kit, and emergency contacts posted (Safety)

☐  Confirm sponsor recognition materials (banners, signage) are printed (Marketing)

# 7 Days Before Event

☐  Reconfirm vendor headcount and booth assignments (Vendors)

☐  Reconfirm volunteer shift coverage; fill any gaps (Volunteers)

☐  Confirm final cash handling assignments and two-person count teams (Cash Handling)

☐  Confirm weather contingency plan (Safety)

☐  Prepare Cash Count Sheets, receipt books, and donation forms for event day (Documentation)

☐  Finalize social media and press outreach push (Marketing)

# Day Before Event

☐  Set up tables, tents, signage, and vendor booth markers on-site if possible (Vendors)

☐  Deliver or stage bake sale, contest, and other special-activity supplies, as applicable (Donations)

☐  Confirm all cash boxes are counted, recorded, and secured for the next day (Cash Handling)

☐  Brief committee leads on final schedule and roles (Documentation)

☐  Confirm signage for FDACS disclosure statement is included on any printed solicitation materials (Documentation)

# Event Day

☐  Vendor check-in and booth assignment (Vendors)

☐  Volunteer check-in and shift assignment (Volunteers)

☐  Starting cash fund count — two-person verification for each cash box (Cash Handling)

☐  Collect signed Hold Harmless Agreements / Waivers from any day-of vendors or volunteers (Documentation / Safety)

☐  Monitor bake sale/contest activities and vendor booths throughout the event (Vendors)

☐  Collect in-kind and cash donations using proper receipt procedures (Donations / Cash Handling)

☐  Monitor parking, foot traffic, and general safety (Safety)

☐  Capture photos/video per signed media releases (Marketing / Documentation)

☐  End-of-day two-person cash count and secure storage (Cash Handling)

# Post-Event Follow-Up

☐  Complete final cash reconciliation and bank deposit within 2 business days (Cash Handling)

☐  Send thank-you and donation acknowledgment letters to sponsors and donors (Donations / Documentation)

☐  Send thank-you notes to vendors and volunteers (Vendors / Volunteers)

☐  Compile event financial summary and impact metrics for the Board (Documentation)

☐  Post event recap and thank-you on social media (Marketing)

☐  Debrief with the Fundraiser Committee — capture lessons learned for next year (Documentation)

☐  File all signed forms (waivers, hold harmless agreements, cash count sheets, donation forms) per AGHF Inc. record retention standards (Documentation)